# Steering Committee Report 02

## STEERING COMMITTEE REPORT

=========================

Meeting: ERP Steering Committee

Date: May 27, 2026

Time: 10:00 AM - 12:00 PM

Location: Executive Conference Room, Corporate HQ

Attendees: William Harrison (CFO), Richard Anderson (General Counsel), Patricia Williams (CFO), Robert Johnson (Project Manager), Maria Garcia (Data Migration Lead), David Lee (Change Management Lead)

Absent: None

Minutes Prepared By: Robert Johnson, Senior Project Manager

Report Period: May 2026

## EXECUTIVE SUMMARY

-----------------

The ERP Steering Committee met to address critical issues with the SAP S/4HANA implementation. The project is experiencing significant challenges with data quality, vendor performance, and timeline delays. The committee approved a timeline extension to July 30, 2026, activated contingency budget of $250,000, and authorized weekend work for data cleansing. Two critical escalations were discussed requiring immediate executive intervention.

## PROJECT STATUS OVERVIEW

-----------------------

Project: SAP S/4HANA Implementation - Phase 1

Overall Status: AMBER

Schedule Variance: -15% (Behind schedule)

Cost Variance: +5% (Over budget)

Quality Index: 85% (Acceptable)

## Critical Issues:

- Data quality issues causing extended migration timeline

- Vendor resource availability concerns

- Business stakeholder availability blocking requirements validation

- Budget utilization at 95% with contingency activated

## EXECUTIVE DECISIONS MADE

-------------------------

Decision 1: Timeline Extension Approval

Date: May 27, 2026

Decision: Approved timeline extension to July 30, 2026 for SAP S/4HANA Phase 1 go-live

Rationale: Data quality issues cannot be rushed, integration complexity requires additional time, business readiness concerns

Impact: Business planning, resource allocation, budget impact, vendor contract implications

Voting: Unanimous approval with conditions

Conditions: Weekly status reports, monthly budget reviews, go-live readiness assessment by June 25

Decision Maker: William Harrison, CFO

Decision 2: Contingency Budget Activation

Date: May 27, 2026

Decision: Activated contingency budget of $250,000 to cover additional data cleansing resources and weekend work

Rationale: Unforeseen data quality issues require additional investment, timeline extension necessitates additional resources

Impact: Financial resources, team capacity, weekend compensation

Voting: Unanimous approval

Decision Maker: Patricia Williams, CFO

Decision 3: Weekend Work Authorization

Date: May 27, 2026

Decision: Authorized weekend work for data cleansing team to accelerate timeline recovery

Rationale: Critical path activities require acceleration, data cleansing is blocking progress

Impact: Team capacity, additional cost, timeline recovery

Voting: Unanimous approval

Decision Maker: William Harrison, CFO

Decision 4: Vendor Contract Escalation Authorization

Date: May 27, 2026

Decision: Authorized formal escalation to vendor executive leadership regarding resource quality and availability issues

Rationale: Vendor performance below contractual standards, critical path at risk

Impact: Vendor relationship, potential contract penalties, alternative vendor evaluation

Voting: Unanimous approval

Decision Maker: Richard Anderson, General Counsel

## ESCALATIONS REVIEWED

-------------------

Escalation 1: Data Quality Crisis Blocking Migration

Escalated By: Maria Garcia, Data Migration Lead

Escalation Date: May 22, 2026

Issue: Legacy system data contains significant quality issues preventing successful migration, requiring extensive manual intervention

Impact: Migration timeline extended by 4 weeks, additional $300,000 in costs, go-live at risk

Committee Action: Approved contingency budget activation, authorized weekend work, engaged external data consultants

Resolution: In progress, daily monitoring required

Status: Active - Critical

Escalation 2: Business Stakeholder Unavailability Blocking Requirements

Escalated By: Robert Johnson, Project Manager

Escalation Date: May 24, 2026

Issue: Finance Director unavailable for critical requirements validation due to competing priorities

Impact: Potential requirements rework, timeline impact, governance failure

Committee Action: Escalated to CFO for intervention, authorized executive mandate for stakeholder participation

Resolution: CFO to engage Finance Director directly

Status: Active - High Priority

Escalation 3: Vendor Resource Quality Below Contractual Standards

Escalated By: Robert Johnson, Project Manager

Escalation Date: May 25, 2026

Issue: Vendor providing junior resources instead of senior architects as specified in contract

Impact: Quality concerns, technical leadership gap, potential rework, timeline impact

Committee Action: Authorized formal contract escalation, legal team to assess breach, backup vendor evaluation initiated

Resolution: Vendor executive meeting scheduled for May 28

Status: Active - High Priority

## FUNDING APPROVALS

-----------------

Approval 1: Data Cleansing Resources Augmentation

Amount: $150,000

Purpose: Additional data cleansing resources and external consultants

Budget Source: Contingency budget

Approval Status: Approved

Approving Executive: Patricia Williams, CFO

Approval 2: Weekend Work Compensation

Amount: $50,000

Purpose: Compensation for weekend work for data cleansing team

Budget Source: Contingency budget

Approval Status: Approved

Approving Executive: Patricia Williams, CFO

Approval 3: External Data Consultants Engagement

Amount: $50,000

Purpose: Engagement of external data quality consultants

Budget Source: Contingency budget

Approval Status: Approved

Approving Executive: Patricia Williams, CFO

## RESOURCE APPROVALS

------------------

Approval 1: Additional Data Migration Resources

Request: 4 additional data migration specialists for 8 weeks

Purpose: Accelerate data cleansing and migration

Cost: $120,000 (including weekend work)

Approval Status: Approved

Approving Executive: William Harrison, CFO

Approval 2: Change Management Team Augmentation

Request: 2 additional change management specialists for 6 weeks

Purpose: Accelerate user training and adoption

Cost: $75,000

Approval Status: Approved

Approving Executive: Amanda Foster, COO

## VENDOR GOVERNANCE

-----------------

Vendor Review: SAP (Primary ERP Vendor)

Status: Concerns noted

Performance Metrics: Technical support adequate, resource quality below standards

Issues: Resource quality concerns, availability constraints

Action Items: Formal escalation to SAP executive leadership, contract breach assessment, backup vendor evaluation

Vendor Review: Data Migration Consulting Firm

Status: Satisfactory

Performance Metrics: On-time delivery, quality acceptable

Issues: None

Action Items: Continue current engagement, expand scope if needed

## RISK OVERVIEW

-------------

Current Risk Count: 4 (0 Mitigated, 2 Monitoring, 2 Active)

High Priority Risks: 2

Critical Risks: 0

Risk Trend: Increasing

## Key Risks:

- Data quality issues: Active - Critical

- Vendor resource availability: Active - High

- User adoption resistance: Monitoring

- Integration complexity: Monitoring

## ACTION ITEMS FROM COMMITTEE

---------------------------

Action 1: CFO to engage Finance Director for requirements validation

Owner: Patricia Williams, CFO

Due Date: May 29, 2026

Status: Pending

Action 2: Legal team to complete vendor contract breach assessment

Owner: Richard Anderson, General Counsel

Due Date: June 5, 2026

Status: In Progress

Action 3: Complete data cleansing for Finance module

Owner: Maria Garcia, Data Migration Lead

Due Date: June 5, 2026

Status: In Progress

Action 4: Conduct vendor executive sponsor meeting

Owner: Robert Johnson, Project Manager

Due Date: May 28, 2026

Status: Scheduled

## NEXT MEETING

------------

Date: June 3, 2026 (Special Meeting)

Time: 10:00 AM - 11:30 AM

Location: Executive Conference Room

Agenda: Data quality progress review, vendor escalation outcome, stakeholder engagement status

REPORT SUBMITTED BY: Robert Johnson, Senior Project Manager

DATE: May 27, 2026