# Meeting Minutes 02

## MEETING MINUTES

===============

Meeting: Sprint Review Meeting

Project: Mobile Banking App Redesign

Date: May 27, 2026

Time: 2:00 PM - 3:30 PM

Location: Virtual Meeting (Teams)

Meeting Facilitator: Christopher Lee, Project Manager

Minutes Prepared By: Christopher Lee

## ATTENDEES

---------

Christopher Lee (Project Manager)

Amanda Foster (Product Owner)

David Rodriguez (Lead Developer)

Sarah Kim (UX Designer)

Michael Brown (QA Lead)

Jennifer Adams (Scrum Master)

## ABSENT

None

## AGENDA

------

1. Sprint 3 demo and review

2. Sprint metrics analysis

3. Retrospective discussion

4. Sprint 4 planning

5. Resource updates

6. Questions and concerns

## DISCUSSION

----------

Item 1: Sprint 3 demo and review

## David Rodriguez demonstrated Sprint 3 deliverables:

- Account balance view: Completed and demonstrated

- Transaction history: Completed with minor UI adjustments needed

- Bill payment functionality: 90% complete, pending final testing

- Mobile check deposit: 75% complete, on track

- Settings and preferences: Completed

Amanda Foster provided feedback on transaction history UI, requesting additional filtering options. Team agreed to add to Sprint 4 backlog.

Item 2: Sprint metrics analysis

## Jennifer Adams presented Sprint 3 metrics:

- Story points completed: 42 of 45 planned (93%)

- Velocity: Stable, consistent with previous sprints

- Defect count: 3 minor defects, all resolved

- Sprint goal achievement: 80% (bill payment slightly behind)

Team discussed bill payment delay and identified root cause as third-party API documentation gaps.

Item 3: Retrospective discussion

## Team conducted retrospective:

## What went well:

- Strong collaboration between UX and development

- Improved defect detection in early testing

- Clear communication channels

## What could be improved:

- Third-party API integration challenges

- Time estimation for external dependencies

- Documentation completeness

Action items: Improve API documentation process, add buffer for external dependencies.

Item 4: Sprint 4 planning

## Team planned Sprint 4 (May 30 - June 13):

- Complete bill payment functionality

- Finish mobile check deposit

- Add transaction filtering

- Implement push notifications

- Performance optimization

Story points committed: 48 points

Team capacity: 8 developers × 2 weeks = available capacity confirmed

Item 5: Resource updates

## Christopher Lee provided resource updates:

- iOS developer position still vacant, contractor engaged as interim

- UX designer capacity confirmed for Sprint 4

- QA team capacity adequate

Amanda Foster noted that iOS development lag may impact Sprint 5 planning.

Item 6: Questions and concerns

Sarah Kim raised concern about accessibility compliance timeline. Team agreed to include accessibility testing in Sprint 4.

## ACTION ITEMS

------------

1. Complete bill payment functionality - David Rodriguez (Due: June 10)

2. Add transaction filtering to backlog - Amanda Foster (Due: May 28)

3. Improve API documentation process - David Rodriguez (Due: June 1)

4. Include accessibility testing in Sprint 4 - Michael Brown (Due: June 13)

5. Follow up on iOS developer hiring - Christopher Lee (Due: June 5)

## NEXT MEETING

-----------

Date: June 3, 2026

Time: 2:00 PM - 3:00 PM

Location: Virtual Meeting

Agenda: Sprint 4 progress check, iOS hiring update

MINUTES APPROVED BY: Christopher Lee, Project Manager

DATE: May 27, 2026