# Meeting Minutes 04

## MEETING MINUTES

===============

Meeting: Vendor Management Meeting

Project: Supply Chain Modernization

Date: May 27, 2026

Time: 11:00 AM - 12:00 PM

Location: Vendor Management Office

Meeting Facilitator: Kevin Martinez, Program Manager

Minutes Prepared By: Kevin Martinez

## ATTENDEES

---------

Kevin Martinez (Program Manager)

Procurement Director

Legal Department Representative

IT Director

Vendor Account Manager (TechGlobal Solutions)

Quality Assurance Lead

## ABSENT

None

## AGENDA

------

1. Vendor performance review

2. Contract compliance discussion

3. Delivery timeline concerns

4. Quality metrics review

5. Next steps and action items

## DISCUSSION

----------

Item 1: Vendor performance review

## Kevin Martinez presented TechGlobal Solutions performance:

- On-time delivery: 60% (below 90% target)

- Quality metrics: 88% (meets minimum requirements)

- Communication: Adequate but response time increased

- Resource quality: Below contractual standards

Vendor Account Manager acknowledged performance issues and cited resource constraints as primary cause.

Item 2: Contract compliance discussion

## Legal Representative reviewed contract compliance:

- Resource level requirements: Not met (junior vs. senior resources)

- Delivery timeline: Missed by 3 weeks on Module A

- Quality standards: Met minimum but not excellence targets

- Communication SLA: Met

Legal team noted potential contract breach regarding resource levels.

Item 3: Delivery timeline concerns

## IT Director raised concerns about delivery timeline impact:

- Module A delay: 3 weeks late, now promised June 10

- Module B status: At risk for similar delay

- Integration testing: Postponed due to Module A delay

- Overall project timeline: 4-week delay projected

Vendor Account Manager committed to accelerated delivery for Module B.

Item 4: Quality metrics review

## Quality Assurance Lead presented quality metrics:

- Defect rate: 12% (above 8% target)

- Rejection rate: 5% (acceptable)

- Documentation completeness: 75% (below 90% target)

- Code review pass rate: 85% (acceptable)

Team agreed to implement enhanced quality gates for remaining deliverables.

Item 5: Next steps and action items

## Kevin Martinez summarized next steps:

- Vendor executive meeting scheduled for May 28

- Performance improvement plan required from vendor

- Contract penalty calculation in progress

- Backup vendor evaluation initiated

Vendor Account Manager agreed to provide performance improvement plan by May 30.

## ACTION ITEMS

------------

1. Attend vendor executive meeting - Kevin Martinez, Procurement Director (Due: May 28)

2. Provide performance improvement plan - Vendor Account Manager (Due: May 30)

3. Complete contract penalty calculation - Legal Representative (Due: June 1)

4. Implement enhanced quality gates - Quality Assurance Lead (Due: June 5)

5. Evaluate backup vendor options - Procurement Director (Due: June 5)

## NEXT MEETING

-----------

Date: June 5, 2026

Time: 11:00 AM - 12:00 PM

Location: Vendor Management Office

Agenda: Performance improvement plan review, vendor decision point

MINUTES APPROVED BY: Kevin Martinez, Program Manager

DATE: May 27, 2026