# Meeting Minutes 07

## MEETING MINUTES

===============

Meeting: Weekly Project Status Meeting

Project: Enterprise Resource Planning Upgrade

Date: May 27, 2026

Time: 9:30 AM - 10:30 AM

Location: Project War Room

Meeting Facilitator: Robert Johnson, Project Manager

Minutes Prepared By: Robert Johnson

## ATTENDEES

---------

Robert Johnson (Project Manager)

Maria Garcia (Data Migration Lead)

David Lee (Change Management Lead)

Technical Lead

Finance Representative

Business Analyst

SAP Consultant

## ABSENT

None

## AGENDA

------

1. Action items review

2. Data migration status

3. Technical progress update

4. Change management activities

5. Risk and issues review

6. Week ahead planning

## DISCUSSION

----------

Item 1: Action items review

## Robert Johnson reviewed action items from May 20 meeting:

- Data cleansing for Finance module: 60% complete, on track

- Stakeholder alignment meeting: Completed, issues resolved

- Budget revision request: Submitted, awaiting approval

- Communication plan update: 80% complete

All action items progressing satisfactorily.

Item 2: Data migration status

## Maria Garcia presented data migration status:

- Total data objects: 150

- Migrated: 112 (75%)

- Validated: 98 (65%)

- Failed: 14 (9%)

- In progress: 24 (16%)

Critical issue: General Ledger data inconsistencies requiring manual correction. Finance team working weekends to resolve.

Item 3: Technical progress update

## Technical Lead presented technical status:

- System configuration: Completed

- Integration development: Completed

- Data migration execution: 75% complete

- Integration testing: 60% complete

- User training environment: Ready

Performance testing revealed minor issues with high-volume transactions, tuning in progress.

Item 4: Change management activities

## David Lee presented change management status:

- Process documentation: 85% complete

- User training: 40% complete (accelerated)

- Super user preparation: 60% complete

- Communication activities: 70% complete

Business stakeholder resistance noted, executive sponsorship engagement requested.

Item 5: Risk and issues review

## Robert Johnson led risk and issues discussion:

- Data quality issues: Active, mitigation in progress

- Vendor resource availability: Active, escalation in progress

- Business stakeholder resistance: Active, executive engagement needed

- Integration performance: Monitoring, tuning in progress

Team agreed to escalate stakeholder resistance to sponsor.

Item 6: Week ahead planning

## Robert Johnson outlined week ahead:

- Complete GL data correction: Priority 1

- Accelerate user training: Priority 2

- Conduct vendor escalation meeting: Priority 3

- Complete integration testing: Priority 4

Team confirmed resource availability for priorities.

## ACTION ITEMS

------------

1. Complete GL data correction - Finance Team (Due: June 5)

2. Accelerate user training completion - Change Management Team (Due: June 20)

3. Conduct vendor escalation meeting - Robert Johnson (Due: May 29)

4. Complete integration testing - Technical Team (Due: June 10)

5. Escalate stakeholder resistance to sponsor - Robert Johnson (Due: May 28)

## NEXT MEETING

-----------

Date: June 3, 2026

Time: 9:30 AM - 10:30 AM

Location: Project War Room

Agenda: Data correction progress, training status, vendor meeting outcome

MINUTES APPROVED BY: Robert Johnson, Project Manager

DATE: May 27, 2026