# Project Status Report 02 Amber

## PROJECT STATUS REPORT

=====================

Project Name: Enterprise Resource Planning Upgrade

Project ID: ERP-2024-089

Report Date: May 27, 2026

Reporting Period: May 20 - May 27, 2026

Prepared By: Robert Johnson, Senior Project Manager

Sponsor: Patricia Williams, CFO

## EXECUTIVE SUMMARY

-----------------

The ERP Upgrade project is experiencing schedule delays due to unexpected data quality issues discovered during the migration testing phase. While the core functionality is progressing well, the data cleansing effort is requiring additional time and resources. Budget utilization is at 95% with contingency funds being activated.

## OVERALL STATUS: AMBER

## PROJECT METRICS

---------------

- Schedule Variance: -15% (Behind schedule)

- Cost Variance: +5% (Over budget)

- Scope Variance: +8% (Scope creep)

- Quality Index: 85% (Acceptable)

- Resource Utilization: 98%

## MILESTONE PROGRESS

------------------

✓ Requirements Analysis - COMPLETED (April 10)

✓ Vendor Selection - COMPLETED (April 25)

✓ System Configuration - COMPLETED (May 15)

✓ Data Migration Planning - COMPLETED (May 20)

⚠ Data Migration Execution - DELAYED (Original: May 25, Revised: June 8)

○ User Acceptance Testing - RESCHEDULED (June 15)

○ Go-Live - RESCHEDULED (July 30)

## RISKS

-----

1. Risk: Data quality issues causing extended migration timeline

Impact: High | Probability: High

Status: Active

Owner: Maria Garcia, Data Migration Lead

Mitigation: Additional data cleansing resources allocated, weekend work authorized

2. Risk: User adoption resistance due to timeline changes

Impact: Medium | Probability: Medium

Status: Monitoring

Owner: David Lee, Change Management Lead

Mitigation: Enhanced communication plan activated, training sessions accelerated

3. Risk: Vendor resource availability for critical path activities

Impact: High | Probability: Medium

Status: Active

Owner: Robert Johnson, Project Manager

Mitigation: Vendor contract escalation initiated, backup resources identified

## ISSUES

------

1. Issue: Legacy system data inconsistencies discovered

Severity: High

Status: In Progress

Owner: Maria Garcia

Impact: Migration timeline extended by 2 weeks

Resolution: Additional cleansing scripts being developed

2. Issue: Key business stakeholder unavailable for requirements validation

Severity: Medium

Status: Escalated

Owner: Robert Johnson

Impact: Potential rework risk

Resolution: Escalated to sponsor for intervention

## ACTIONS

-------

1. Complete data cleansing for Finance module - Maria Garcia (Due: June 5, Priority: Critical)

2. Conduct emergency stakeholder alignment meeting - Robert Johnson (Due: May 29, Priority: High)

3. Submit revised budget request - Patricia Williams (Due: June 1, Priority: High)

4. Update communication plan with new timeline - David Lee (Due: May 30, Priority: Medium)

## DEPENDENCIES

------------

- External: Vendor consultant availability - At risk

- Internal: Business stakeholder sign-off - Blocked

- Internal: IT infrastructure readiness - On track

## DECISIONS MADE

-------------

- Approved timeline extension to July 30, 2026 (May 26)

- Activated contingency budget of $250,000 (May 26)

- Authorized weekend work for data cleansing team (May 27)

## RECOMMENDATIONS

---------------

1. Immediate intervention required from sponsor to secure stakeholder availability

2. Consider phased go-live approach to mitigate timeline risk

3. Increase vendor management oversight

4. Prepare contingency communication for business users

ESCALATION REQUIRED: Yes - Timeline and budget variance require steering committee attention

NEXT REPORT DATE: June 3, 2026 (Special report requested)