# Project Status Report 05 Budget Overrun

## PROJECT STATUS REPORT

=====================

Project Name: Global Compliance System

Project ID: GCS-2024-203

Report Date: May 27, 2026

Reporting Period: May 20 - May 27, 2026

Prepared By: Elizabeth Taylor, Project Manager

Sponsor: Richard Anderson, General Counsel

## EXECUTIVE SUMMARY

-----------------

The Global Compliance System project has exceeded its approved budget by 40% due to scope expansion and unexpected regulatory requirements. While the project is delivering high-value outcomes and is on schedule, the financial variance requires immediate attention. A budget augmentation request has been submitted and is pending executive approval. The project team has implemented cost control measures for remaining work.

## OVERALL STATUS: AMBER

## PROJECT METRICS

---------------

- Schedule Variance: +5% (Ahead of schedule)

- Cost Variance: +40% (Significantly over budget)

- Scope Variance: +35% (Significant scope expansion)

- Quality Index: 95% (Excellent)

- Resource Utilization: 95%

## MILESTONE PROGRESS

------------------

✓ Regulatory Requirements Analysis - COMPLETED (March 30)

✓ System Architecture - COMPLETED (April 20)

✓ Core Development - COMPLETED (May 15)

✓ Multi-jurisdiction Compliance Rules - COMPLETED (May 25)

○ Integration Testing - IN PROGRESS (Due June 5)

○ Regional Deployment - SCHEDULED (June 20)

○ Global Rollout - SCHEDULED (July 15)

## BUDGET STATUS

-------------

Original Budget: $2,500,000

Current Spend: $3,500,000

Variance: +$1,000,000 (+40%)

Remaining Work Estimate: $600,000

Total Projected Cost: $4,100,000

Budget Augmentation Requested: $1,600,000

## RISKS

-----

1. Risk: Budget augmentation not approved by executive committee

Impact: Critical | Probability: Medium

Status: Active

Owner: Elizabeth Taylor, Project Manager

Mitigation: Cost reduction plan developed, phased delivery option prepared

2. Risk: Additional regulatory requirements discovered in remaining jurisdictions

Impact: High | Probability: Medium

Status: Monitoring

Owner: Richard Anderson, General Counsel

Mitigation: Contingency budget allocated, regulatory engagement accelerated

3. Risk: Audit findings require system modifications post-deployment

Impact: Medium | Probability: Low

Status: Monitoring

Owner: Compliance Team

Mitigation: Early auditor engagement, flexible architecture maintained

## ISSUES

------

1. Issue: GDPR compliance requirements more complex than anticipated

Severity: High

Status: Resolved with scope expansion

Owner: Elizabeth Taylor

Impact: Additional $300,000 in development costs

Resolution: Scope approved, budget augmentation requested

2. Issue: Asia-Pacific regulatory framework changed during project

Severity: High

Status: Resolved with scope expansion

Owner: Richard Anderson

Impact: Additional $450,000 for regional adaptation

Resolution: New requirements incorporated, budget augmentation requested

3. Issue: Third-party data provider costs increased by 50%

Severity: Medium

Status: Negotiation in progress

Owner: Procurement Team

Impact: Potential $150,000 additional annual cost

Resolution: Alternative providers being evaluated

## ACTIONS

-------

1. Present budget augmentation request to Executive Committee - Elizabeth Taylor (Due: May 30, Priority: Critical)

2. Develop cost reduction plan for remaining work - Elizabeth Taylor (Due: June 1, Priority: High)

3. Complete alternative data provider evaluation - Procurement Team (Due: June 5, Priority: Medium)

4. Prepare phased delivery option if full funding not approved - Elizabeth Taylor (Due: June 3, Priority: High)

## DEPENDENCIES

------------

- Internal: Budget augmentation approval - CRITICAL

- External: Data provider contract renewal - At risk

- Internal: Regulatory sign-off - On track

## DECISIONS MADE

-------------

- Approved scope expansion for GDPR and APAC requirements (May 20)

- Authorized budget augmentation request preparation (May 22)

- Implemented cost control measures for remaining work (May 25)

## RECOMMENDATIONS

---------------

1. Executive committee decision on budget augmentation required urgently

2. Consider phased rollout to manage cash flow if full augmentation not approved

3. Strengthen budget governance for future regulatory projects

4. Document lessons learned on regulatory complexity estimation

FINANCIAL ESCALATION: Yes - Budget augmentation requires CFO and CEO approval

NEXT REPORT DATE: June 3, 2026