# Project Status Report 07 Uat Issues

## PROJECT STATUS REPORT

=====================

Project Name: Claims Processing System Upgrade

Project ID: CPS-2024-112

Report Date: May 27, 2026

Reporting Period: May 20 - May 27, 2026

Prepared By: Nancy White, Delivery Manager

Sponsor: Brian Thompson, VP of Claims Operations

## EXECUTIVE SUMMARY

-----------------

The Claims Processing System Upgrade project has entered User Acceptance Testing (UAT) phase with significant issues being discovered by business users. While development was completed on schedule and within budget, UAT has revealed critical defects in claims calculation logic and integration with external systems. The project team is working intensively to resolve issues, but go-live timeline is at risk. Business user confidence has been impacted.

## OVERALL STATUS: AMBER

## PROJECT METRICS

---------------

- Schedule Variance: -10% (UAT delays)

- Cost Variance: +8% (Defect remediation costs)

- Scope Variance: 0% (No changes)

- Quality Index: 65% (UAT issues)

- Resource Utilization: 105% (Remediation surge)

## MILESTONE PROGRESS

------------------

✓ Requirements Gathering - COMPLETED (February 28)

✓ System Design - COMPLETED (March 30)

✓ Development - COMPLETED (May 10)

✓ System Testing - COMPLETED (May 15)

⚠ User Acceptance Testing - IN PROGRESS (Critical issues found)

○ Defect Remediation - IN PROGRESS

○ Performance Testing - BLOCKED (Awaiting UAT completion)

○ Go-Live - AT RISK (Original: June 15, Potential: July 1)

## UAT STATUS SUMMARY

------------------

UAT Started: May 16

Test Cases Executed: 245 of 300 (82%)

Test Cases Passed: 180 (74%)

Test Cases Failed: 65 (26%)

Critical Defects: 12

Major Defects: 23

Minor Defects: 30

## CRITICAL UAT ISSUES

------------------

1. Issue: Claims calculation engine producing incorrect amounts for complex multi-line claims

Severity: Critical

Status: Under investigation

Owner: Development Team

Impact: Financial accuracy, regulatory compliance

Root Cause: Logic error in discount application algorithm

Resolution: Code fix in progress, regression testing required

2. Issue: Integration with external payment gateway failing intermittently

Severity: Critical

Status: Vendor support engaged

Owner: Integration Team

Impact: Payment processing capability

Root Cause: API timeout configuration issue

Resolution: Vendor patch expected May 30

3. Issue: Batch processing jobs failing for high-volume claim batches

Severity: Critical

Status: Performance tuning in progress

Owner: Architecture Team

Impact: Processing capacity for peak periods

Root Cause: Memory leak in batch processor

Resolution: Hotfix being tested

## RISKS

-----

1. Risk: UAT cannot be completed by scheduled go-live date

Impact: High | Probability: High

Status: Active

Owner: Nancy White, Delivery Manager

Mitigation: Go-live contingency dates identified, remediation team expanded

2. Risk: Business user confidence eroding due to quality issues

Impact: Medium | Probability: Medium

Status: Active

Owner: Brian Thompson, Sponsor

Mitigation: Daily status calls, transparent communication, user involvement in testing

3. Risk: Regulatory audit findings if defects not resolved before go-live

Impact: High | Probability: Low

Status: Monitoring

Owner: Compliance Team

Mitigation: Compliance review of all fixes, audit trail maintained

## ISSUES

------

1. Issue: Critical defects exceeding remediation capacity

Severity: High

Status: Resource augmentation requested

Owner: Nancy White

Impact: Extended timeline required

Resolution: Additional developers allocated from other projects

2. Issue: UAT test environment instability affecting testing

Severity: Medium

Status: Infrastructure team engaged

Owner: Infrastructure Team

Impact: Testing delays, user frustration

Resolution: Environment refresh scheduled, additional capacity allocated

## ACTIONS

-------

1. Complete root cause analysis for claims calculation issue - Development Lead (Due: May 29, Priority: Critical)

2. Implement and test code fix for calculation engine - Development Team (Due: June 1, Priority: Critical)

3. Coordinate vendor patch deployment for payment gateway - Integration Team (Due: May 30, Priority: Critical)

4. Conduct regression testing for all critical fixes - QA Team (Due: June 5, Priority: High)

5. Prepare go-live decision recommendation - Nancy White (Due: June 8, Priority: High)

## DEPENDENCIES

------------

- External: Payment gateway vendor patch - Expected May 30

- Internal: UAT user availability - Coordinated

- Internal: Remediation team capacity - Augmented

## DECISIONS MADE

-------------

- UAT extended by 2 weeks (May 25)

- Additional resources allocated to defect remediation (May 26)

- Go-live contingency dates of July 1 and July 15 identified (May 27)

## RECOMMENDATIONS

---------------

1. Consider phased go-live with limited functionality if all critical defects cannot be resolved

2. Increase business user involvement in defect validation

3. Prepare rollback plan in case go-live needs to be postponed

4. Conduct post-mortem on quality assurance process

UAT ESCALATION: Yes - Critical UAT issues require sponsor and operations leadership attention

NEXT REPORT DATE: June 3, 2026 (Daily UAT status reports)