# Project Status Report 08 Infrastructure Dependency

## PROJECT STATUS REPORT

=====================

Project Name: Data Lake Implementation

Project ID: DLI-2024-095

Report Date: May 27, 2026

Reporting Period: May 20 - May 27, 2026

Prepared By: Mark Johnson, Infrastructure Project Manager

Sponsor: Susan Clark, Chief Data Officer

## EXECUTIVE SUMMARY

-----------------

The Data Lake Implementation project is blocked by critical infrastructure dependencies. The required cloud infrastructure provisioning is significantly delayed due to internal process issues and cloud provider capacity constraints. While the project team is ready to begin development and data ingestion work, they cannot proceed without the foundational infrastructure. The project timeline is at risk, and the team is exploring alternative approaches.

## OVERALL STATUS: AMBER

## PROJECT METRICS

---------------

- Schedule Variance: -30% (Infrastructure delays)

- Cost Variance: -10% (Under budget - work not started)

- Scope Variance: 0% (No changes)

- Quality Index: N/A (Development not started)

- Resource Utilization: 40% (Team waiting on infrastructure)

## MILESTONE PROGRESS

------------------

✓ Business Requirements - COMPLETED (April 10)

✓ Data Architecture Design - COMPLETED (April 30)

✓ Technology Stack Selection - COMPLETED (May 15)

⚠ Cloud Infrastructure Provisioning - BLOCKED (6 weeks delay)

⚠ Network Security Configuration - BLOCKED (Awaiting infrastructure)

⚠ Data Ingestion Pipelines - NOT STARTED (Infrastructure dependent)

⚠ Data Transformation Layer - NOT STARTED (Infrastructure dependent)

○ Data Quality Framework - NOT STARTED

○ Governance Implementation - NOT STARTED

○ Go-Live - INDEFINITELY DELAYED

## INFRASTRUCTURE DEPENDENCIES

---------------------------

1. Cloud Provider Account Setup

Status: COMPLETED

Dependency: None

2. Virtual Network Configuration

Status: BLOCKED

Original Due: April 20

Current Status: Awaiting Cloud Provider Capacity

Delay: 5 weeks

Owner: Cloud Infrastructure Team

3. Storage Tier Provisioning (5 PB total)

Status: BLOCKED

Original Due: May 5

Current Status: Internal approval process stalled

Delay: 3 weeks

Owner: IT Finance Committee

4. Compute Cluster Setup (50 nodes)

Status: BLOCKED

Original Due: May 15

Current Status: Awaiting Network Configuration

Delay: 2 weeks

Owner: Cloud Infrastructure Team

5. Security Certificate Provisioning

Status: IN PROGRESS

Due: June 10

Owner: Security Team

## RISKS

-----

1. Risk: Infrastructure delays may extend beyond project timeline

Impact: Critical | Probability: High

Status: Critical

Owner: Mark Johnson, Project Manager

Mitigation: Alternative cloud region evaluation, hybrid architecture consideration

2. Risk: Cloud provider capacity constraints may require multi-region approach

Impact: High | Probability: Medium

Status: Active

Owner: Cloud Architecture Team

Mitigation: Multi-region architecture designed, additional budget requested

3. Risk: Team resources idle while waiting for infrastructure

Impact: Medium | Probability: Certain

Status: Active

Owner: Mark Johnson, Project Manager

Mitigation: Team reassigned to other projects temporarily, recall planned

4. Risk: Business stakeholders lose confidence due to delays

Impact: Medium | Probability: Medium

Status: Monitoring

Owner: Susan Clark, Sponsor

Mitigation: Regular communication, alternative timeline presented

## ISSUES

------

1. Issue: Cloud Infrastructure Team unable to meet provisioning timeline

Severity: Critical

Status: Escalated to CIO

Owner: Mark Johnson

Impact: Project completely blocked

Resolution: CIO intervention requested, external cloud consultants engaged

2. Issue: IT Finance Committee approval for storage costs stalled

Severity: High

Status: Escalated to CFO

Owner: Susan Clark, Sponsor

Impact: Cannot provision required storage capacity

Resolution: CFO meeting scheduled for May 30

3. Issue: Cloud provider reporting capacity constraints in primary region

Severity: High

Status: Alternative evaluation in progress

Owner: Cloud Architecture Team

Impact: May require architecture redesign

Resolution: Secondary region assessment underway

## ACTIONS

-------

1. Complete alternative cloud region evaluation - Cloud Architecture Team (Due: June 1, Priority: Critical)

2. Present storage cost business case to CFO - Susan Clark (Due: May 30, Priority: Critical)

3. Develop hybrid cloud architecture as contingency - Cloud Architecture Team (Due: June 5, Priority: High)

4. Update project timeline with infrastructure dependency critical path - Mark Johnson (Due: May 29, Priority: High)

## DEPENDENCIES

------------

- External: Cloud Provider Capacity - CRITICAL CONSTRAINT

- Internal: IT Finance Committee Approval - BLOCKED

- Internal: Cloud Infrastructure Team Delivery - BLOCKED

- Internal: Security Team Certificates - On track

## DECISIONS MADE

-------------

- Approved evaluation of alternative cloud regions (May 23)

- Authorized engagement of external cloud consultants (May 25)

- Approved team reassignment to other projects temporarily (May 26)

## RECOMMENDATIONS

---------------

1. Immediate CIO intervention required for infrastructure team capacity

2. Consider accelerating multi-region approach to bypass capacity constraints

3. Evaluate on-premises hybrid option if cloud delays continue

4. Implement infrastructure governance improvements

INFRASTRUCTURE ESCALATION: Yes - Critical infrastructure blocking requires CIO and CFO attention

NEXT REPORT DATE: June 3, 2026