# Project Status Report 09 Cloud Migration

## PROJECT STATUS REPORT

=====================

Project Name: Enterprise Cloud Migration

Project ID: ECM-2024-188

Report Date: May 27, 2026

Reporting Period: May 20 - May 27, 2026

Prepared By: Daniel Rodriguez, Cloud Migration Lead

Sponsor: Patricia Evans, CTO

## EXECUTIVE SUMMARY

-----------------

The Enterprise Cloud Migration project is progressing through the complex multi-phase migration of 200+ applications. Phase 1 (25 applications) has been completed successfully. Phase 2 (50 applications) is currently in progress with 30 applications migrated and 20 in progress. Technical challenges have been encountered with legacy applications requiring significant refactoring. The project is slightly behind schedule but within budget. Business continuity has been maintained throughout.

## OVERALL STATUS: AMBER

## PROJECT METRICS

---------------

- Schedule Variance: -12% (Legacy application complexity)

- Cost Variance: -5% (Under budget)

- Scope Variance: +5% (Additional legacy apps identified)

- Quality Index: 92% (Good)

- Resource Utilization: 88%

## MILESTONE PROGRESS

------------------

✓ Discovery & Assessment - COMPLETED (February 28)

✓ Cloud Architecture Design - COMPLETED (March 30)

✓ Landing Zone Setup - COMPLETED (April 20)

✓ Phase 1 Migration (25 apps) - COMPLETED (May 10)

○ Phase 2 Migration (50 apps) - IN PROGRESS (60% complete)

○ Phase 3 Migration (75 apps) - SCHEDULED (July 15)

○ Phase 4 Migration (50 apps) - SCHEDULED (September 1)

○ Legacy Application Retirement - SCHEDULED (November 30)

## MIGRATION STATUS

----------------

Total Applications: 200

Migrated: 55 (28%)

In Progress: 20 (10%)

Not Started: 125 (62%)

Successfully Running in Cloud: 53

Issues Identified: 2

Rollbacks Required: 0

## PHASE 2 DETAILS

---------------

Completed: 30 applications

In Progress: 20 applications

Blocked: 0 applications

Average Migration Time: 4 days (Target: 3 days)

Success Rate: 97%

## RISKS

-----

1. Risk: Legacy applications requiring more refactoring than estimated

Impact: High | Probability: High

Status: Active

Owner: Daniel Rodriguez, Migration Lead

Mitigation: Additional refactoring resources allocated, timeline adjusted

2. Risk: Application dependencies not fully documented causing migration issues

Impact: Medium | Probability: Medium

Status: Monitoring

Owner: Architecture Team

Mitigation: Dependency mapping accelerated, testing expanded

3. Risk: Cloud cost overruns due to inefficient resource sizing

Impact: Medium | Probability: Medium

Status: Monitoring

Owner: Cloud FinOps Team

Mitigation: Cost monitoring implemented, right-sizing reviews scheduled

4. Risk: Business disruption during critical application cutover

Impact: High | Probability: Low

Status: Monitoring

Owner: Operations Team

Mitigation: Detailed cutover plans, rollback procedures tested

## ISSUES

------

1. Issue: Legacy ERP system requiring complete re-architecture for cloud compatibility

Severity: High

Status: Architecture assessment in progress

Owner: Enterprise Architecture Team

Impact: Phase 3 timeline at risk, additional budget required

Resolution: Re-architecture plan being developed, vendor consultation initiated

2. Issue: Database migration performance slower than expected for large tables

Severity: Medium

Status: Optimization in progress

Owner: Database Team

Impact: Migration windows extending

Resolution: Alternative migration tools being evaluated, parallel processing increased

## ACTIONS

-------

1. Complete legacy ERP re-architecture assessment - Enterprise Architecture Team (Due: June 5, Priority: High)

2. Optimize database migration process for large tables - Database Team (Due: June 1, Priority: High)

3. Conduct cost optimization review for migrated applications - FinOps Team (Due: June 3, Priority: Medium)

4. Update Phase 3 timeline based on legacy application complexity - Daniel Rodriguez (Due: June 8, Priority: Medium)

## DEPENDENCIES

------------

- External: Cloud provider support tickets - On track

- Internal: Application owner availability - Coordinated

- Internal: Refactoring team capacity - Augmented

- Internal: Cutover window approvals - Secured

## DECISIONS MADE

-------------

- Approved additional refactoring resources for Phase 2 (May 22)

- Authorized legacy ERP re-architecture assessment (May 24)

- Approved Phase 2 timeline extension of 2 weeks (May 26)

## RECOMMENDATIONS

---------------

1. Consider modernization instead of lift-and-shift for complex legacy applications

2. Increase application owner engagement in migration planning

3. Implement automated cost optimization for cloud resources

4. Prepare contingency plans for Phase 3 critical applications

MIGRATION COMPLEXITY: High - Legacy application complexity exceeding estimates

NEXT REPORT DATE: June 3, 2026