## RAID Register
ID | Type | Description | Owner | Due Date | Status | Severity | Mitigation
R1 | unknown |  | TBD | TBD | Open | Medium | TBD
R2 | unknown | Allocated additional data cleansing resources (May 12) | TBD | TBD | Open | Medium | TBD
R3 | unknown | Authorized weekend work for cleansing team (May 15) | TBD | TBD | Open | Medium | TBD
R4 | unknown | Developed automated cleansing scripts (May 18) | TBD | TBD | Open | Medium | TBD
R5 | unknown | Implemented data quality dashboards (May 20) | TBD | TBD | Open | Medium | TBD
R6 | unknown | Enhanced communication plan activated (May 16) | TBD | TBD | Open | Medium | TBD
R7 | unknown | Accelerated training session scheduling (May 18) | TBD | TBD | Open | Medium | TBD
R8 | unknown | Increased executive sponsorship visibility (May 20) | TBD | TBD | Open | Medium | TBD
R9 | unknown | Established user feedback channels (May 22) | TBD | TBD | Open | Medium | TBD
R10 | unknown | Contract escalation initiated (May 19) | TBD | TBD | Open | Medium | TBD
R11 | unknown | Vendor executive sponsor meeting scheduled (May 22) | TBD | TBD | Open | Medium | TBD
R12 | unknown | Backup vendor resources identified (May 20) | TBD | TBD | Open | Medium | TBD
R13 | unknown | Critical path activities prioritized (May 21) | TBD | TBD | Open | Medium | TBD
R14 | unknown | Reverse engineering of integrations initiated (May 21) | TBD | TBD | Open | Medium | TBD
R15 | unknown | Additional integration resources allocated (May 23) | TBD | TBD | Open | Medium | TBD
R16 | unknown | Integration testing environment expanded (May 24) | TBD | TBD | Open | Medium | TBD
R17 | unknown |  | TBD | TBD | Open | Medium | TBD
R18 | unknown | Data reconciliation framework developed (May 23) | TBD | TBD | Open | Medium | TBD
R19 | unknown | Business rules for reconciliation defined (May 24) | TBD | TBD | Open | Medium | TBD
R20 | unknown | Automated reconciliation scripts created (May 25) | TBD | TBD | Open | Medium | TBD
R21 | unknown | Business stakeholder validation sessions scheduled (May 27) | TBD | TBD | Open | Medium | TBD
R22 | unknown | Escalated to sponsor Patricia Williams (May 24) | TBD | TBD | Open | Medium | TBD
R23 | unknown | Alternative stakeholder delegation proposed (May 25) | TBD | TBD | Open | Medium | TBD
R24 | unknown | Requirements documentation prepared for review (May 26) | TBD | TBD | Open | Medium | TBD
R25 | unknown | Formal notice issued to vendor (May 25) | TBD | TBD | Open | Medium | TBD
R26 | unknown | Resource replacement requested (May 26) | TBD | TBD | Open | Medium | TBD
R27 | unknown | Quality gates implemented for deliverables (May 27) | TBD | TBD | Open | Medium | TBD
R28 | unknown |  | TBD | TBD | Open | Medium | TBD
R29 | unknown |  | TBD | TBD | Open | Medium | TBD
R30 | unknown |  | TBD | TBD | Open | Medium | TBD
R31 | unknown |  | TBD | TBD | Open | Medium | TBD