## RAID Register
ID | Type | Description | Owner | Due Date | Status | Severity | Mitigation
R1 | unknown |  | TBD | TBD | Open | Medium | TBD
R2 | unknown | Daily vendor standups implemented (May 16) | TBD | TBD | Open | Medium | TBD
R3 | unknown | Penalty clauses activated (May 17) | TBD | TBD | Open | Medium | TBD
R4 | unknown | Backup vendor identified and engaged (May 18) | TBD | TBD | Open | Medium | TBD
R5 | unknown | Critical path activities prioritized (May 19) | TBD | TBD | Open | Medium | TBD
R6 | unknown | Formal notice issued to vendor (May 18) | TBD | TBD | Open | Medium | TBD
R7 | unknown | Resource replacement requested (May 19) | TBD | TBD | Open | Medium | TBD
R8 | unknown | Quality gates implemented for deliverables (May 20) | TBD | TBD | Open | Medium | TBD
R9 | unknown | Internal technical oversight increased (May 21) | TBD | TBD | Open | Medium | TBD
R10 | unknown | Documentation of all delays maintained (May 20) | TBD | TBD | Open | Medium | TBD
R11 | unknown | Communications archive established (May 21) | TBD | TBD | Open | Medium | TBD
R12 | unknown | Legal assessment of contract terms initiated (May 22) | TBD | TBD | Open | Medium | TBD
R13 | unknown | Additional integration resources allocated (May 23) | TBD | TBD | Open | Medium | TBD
R14 | unknown | Integration testing environment expanded (May 24) | TBD | TBD | Open | Medium | TBD
R15 | unknown | Technical architecture review conducted (May 25) | TBD | TBD | Open | Medium | TBD
R16 | unknown |  | TBD | TBD | Open | Medium | TBD
R17 | unknown | Vendor executive sponsor meeting scheduled (May 21) | TBD | TBD | Open | Medium | TBD
R18 | unknown | Penalty clause calculation initiated (May 22) | TBD | TBD | Open | Medium | TBD
R19 | unknown | Backup vendor engagement accelerated (May 23) | TBD | TBD | Open | Medium | TBD
R20 | unknown | Critical path replanning started (May 24) | TBD | TBD | Open | Medium | TBD
R21 | unknown | Formal breach of contract notice issued (May 22) | TBD | TBD | Open | Medium | TBD
R22 | unknown | Resource replacement demanded within 5 days (May 22) | TBD | TBD | Open | Medium | TBD
R23 | unknown | Contract review for termination options initiated (May 23) | TBD | TBD | Open | Medium | TBD
R24 | unknown | Internal senior architect oversight assigned (May 24) | TBD | TBD | Open | Medium | TBD
R25 | unknown | Payment hold authorized on vendor invoices (May 24) | TBD | TBD | Open | Medium | TBD
R26 | unknown | Legal review of payment terms initiated (May 25) | TBD | TBD | Open | Medium | TBD
R27 | unknown | Penalty calculation completed (May 26) | TBD | TBD | Open | Medium | TBD
R28 | unknown |  | TBD | TBD | Open | Medium | TBD
R29 | unknown |  | TBD | TBD | Open | Medium | TBD
R30 | unknown |  | TBD | TBD | Open | Medium | TBD
R31 | unknown |  | TBD | TBD | Open | Medium | TBD