# PMO Weekly Update: Project Apex ERP Transformation

## 1. Executive Summary

Project Apex ERP Transformation is currently at yellow status due to delays in third-party API integrations. The core ledger customization is 90% complete, and data migration testing for Phase 1 has reached 85% success rate. However, external middleware delivery by partner VendorX is 3 weeks overdue, impacting the downstream testing schedule.

## 2. Key Milestones

| Milestone | Target Date | Status |
| --- | --- | --- |
| Core Customization | 2026-05-15 | Completed |
| Middleware Integration | 2026-06-01 | Delayed |
| UAT Phase 1 | 2026-06-15 | At Risk |

## 3. Risks, Actions, Issues, and Dependencies (RAID)

We are tracking several items that require immediate attention from the leadership team:

RISK: Late API delivery from VendorX. Due to resource constraints at VendorX, the API endpoints for inventory sync are delayed. Impact: High. Mitigation: Daily standups with VendorX and preparation of stub services.

ISSUE: Test environment database crash. The QA database instance crashed on Friday, causing 2 days of UAT downtime. Status: Resolved. Action taken: Restored from backup and increased DB storage allocation.

DEPENDENCY: Database schema freeze by DB Admin team. We cannot finalize the API mappings until the DB schema is frozen by the infrastructure team. Due Date: 2026-05-30.

## 4. Escalations

ESCALATION: VendorX SLA breach on Phase 2 deliverables. VendorX has missed their third consecutive delivery checkpoint. We request formal contract penalty clause execution and escalation of this issue. Routing Target: Steering Committee.